## Sheet1
USER STORIES | TASKS | Estimates and Owner | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27 | 2018-05-28 | 2018-05-29 | 2018-05-30 | 2018-05-31 | 2018-06-01 | 2018-06-02
PRIMARY REQUIREMENTS
U001 - Display red chilly menu items | UI - add accordion(?) based list
API - create endpoint to fetch latest menu list
DB - Create collection MenuList
API - Update menu list
UI - API integration for fetching and displaying details
Menu items should have an add to cart button with quantity | UI - add buttons for every items in menu
API - should add and update the dynamic user cart
DB - Temporary cart Collection TempCartList
Cart bucket icon | UI - should show the updated item count on icon
UI - Onclick show the cart list
UI - should maintain INMEMORY cart lists
UI - should be able to fetch cart status upon login/app-start
API - should fetch the list based upon user
Cart list | UI - Should show the added menu items in the list along with price
UI - Should calculate the total along with taxes
UI - Offers/Promos ?
Checkout | UI - Should show a checkout button on the bottom of cart list
UI - Upon click should show the subsequent page
User details form --Input fields UserName Full Name ? Email id Mobile number Address | UI - Should show a form with input field
UI - Input field should have desired validations
UI - Proceed and Place order button
API - Place order endpoint
API - endpoint validations
API - Bill calculation from MenuList Collection
DB - Create collection OrderList
Order Status Tracking | UI - Create placed && kitchen && onway && delivered indicators
UI - Fetch placed order status every 5 mins
API - endpoint for order status api
API - Websocket
API - Update order status endpoint in OrderList Collection
User Profiling? It’s a must | UI API - Create user
UI API - Update user
UI API - Authenticate user
UI API - Login form (validations)
UI API - Session management
UI API - Email to user forgot password?
App Security | Passport (Node) Session management and endpoint protection
Flashers and Images | UI - Should be able to show popups/carousel/icons
API - Should fetch current available promotions
DB - Should store image blobs
App Events | UI - App should be able to store global events like first login/last updation/ is update available/ order flags etc
Splash Screen Icons | UI - add desired functions
Background Tasks | TBD
Detect my location deliver within ~3km
MVP2
Payments
Email To Clients (forgot password user verification)
Push Notifications about offers
Email To RedChilly about orders
?